## 📋 Test Plan
TEST PLAN — E-COMMERCE WEBSITE (ShopEasy)
Manual Testing Project ¦ QA Engineer Portfolio
Project Name | ShopEasy – E-Commerce Web Application | Doc Version | v1.0
Prepared By | Coummaresh A | Date | 17-Feb-2026
Module | End-to-End Manual Testing | Status | Active
Environment | Staging / UAT | Sprint | Sprint-1
1. PROJECT OVERVIEW
Objective | To validate the functional, UI, and integration aspects of the ShopEasy e-commerce web application through structured manual testing.
Application URL | https://shopease-staging.example.com
Testing Type | Functional Testing, Regression Testing, Smoke Testing, UI Testing, Integration Testing
Test Methodology | Black-Box Testing ¦ Equivalence Partitioning ¦ Boundary Value Analysis
2. SCOPE OF TESTING
IN SCOPE |  | OUT OF SCOPE
✅ User Registration & Login (Email, Google OAuth) |  | ❌ Performance / Load Testing
✅ Product Search, Filters & Sorting |  | ❌ Security Penetration Testing
✅ Product Detail Page & Image Gallery |  | ❌ Mobile Native App
✅ Shopping Cart – Add, Remove, Update Quantity |  | ❌ Payment Gateway (Live Mode)
✅ Checkout Process – Address, Payment, Order Confirmation
✅ Order History & Tracking
✅ User Profile Management
✅ Wishlist Functionality
✅ Coupon / Promo Code Application
✅ Admin – Product & Order Management
3. TEST ENVIRONMENT & TOOLS
OS | Windows 11 / macOS Ventura | Browser | Chrome 120, Firefox 121, Edge 119
Test Management | Excel / Google Sheets | Bug Tracking | JIRA / Bugzilla
API Testing | Postman (smoke checks) | Screen Capture | ShareX / Snagit
Test Data | Manually created & DB scripts | Devices | Desktop + Responsive (1366×768, 1920×1080)
4. ENTRY & EXIT CRITERIA
ENTRY CRITERIA |  | EXIT CRITERIA
✅ Requirements document signed off |  | ✅ All planned test cases executed
✅ Test environment is stable & accessible |  | ✅ 95% test cases passed
✅ Test data prepared and available |  | ✅ All Critical/High bugs resolved
✅ Application build deployed to staging |  | ✅ Test Summary Report approved
5. TEST SCHEDULE
Phase | Activities | Start Date | End Date
Phase 1 – Planning | Review requirements, prepare test plan | 17-Feb-2026 | 20-Feb-2026
Phase 2 – Design | Write test cases, RTM mapping | 21-Feb-2026 | 25-Feb-2026
Phase 3 – Execution | Execute test cases, log defects | 26-Feb-2026 | 07-Mar-2026
Phase 4 – Regression | Re-test fixed bugs, regression run | 08-Mar-2026 | 12-Mar-2026
Phase 5 – Sign-off | Final report, UAT support | 13-Mar-2026 | 15-Mar-2026
6. ROLES & RESPONSIBILITIES
Role | Name | Responsibilities | Contact
QA Lead | Ramesh Kumar | Test planning, review, sign-off | ramesh.k@shopease.com
QA Engineer | Coummaresh A | Test case writing, execution, bug reporting | coummaresh.a@shopease.com
Developer | Ajay Kumar | Bug fixing, build deployment | priya.s@shopease.com
Business Analyst | Saravana Velu | Requirements clarification | saravana.v@shopease.com
Project Manager | Sunita Rao | Overall project coordination | sunita.r@shopease.com

## 🧪 Test Cases
TEST CASES — ShopEasy E-Commerce Website
Module-wise Test Cases ¦ Manual Testing ¦ Black-Box Testing
TC ID | Module | Test Case Title | Pre-Conditions | Test Steps | Expected Result | Priority | Test Type | Status | Remarks
📂 MODULE: User Registration
TC_REG_001 | User Registration | Valid user registration with all mandatory fields | Application is accessible Registration page is loaded | 1. Navigate to https://shopease.example.com 2. Click 'Sign Up' 3. Enter First Name: John 4. Enter Last Name: Doe 5. Enter Email: john.doe@test.com 6. Enter Password: Test@1234 7. Confirm Password: Test@1234 8. Click 'Create Account' | User account created successfully Welcome email sent User redirected to dashboard | Critical | Functional | Pass
TC_REG_002 | User Registration | Registration with already existing email | User 'john.doe@test.com' already registered | 1. Navigate to Sign Up page 2. Enter existing email: john.doe@test.com 3. Fill all other fields 4. Click 'Create Account' | Error message displayed: 'Email already registered. Please login or use a different email' | High | Negative | Pass
TC_REG_003 | User Registration | Registration with invalid email format | Registration page is open | 1. Navigate to Sign Up page 2. Enter invalid email: john.doe@ 3. Fill other valid fields 4. Click 'Create Account' | Inline validation error: 'Please enter a valid email address' | High | Negative | Pass
TC_REG_004 | User Registration | Registration with password less than 8 characters | Registration page is open | 1. Navigate to Sign Up page 2. Enter Password: Test@1 (7 chars) 3. Fill other valid fields 4. Click 'Create Account' | Error: 'Password must be at least 8 characters with 1 uppercase, 1 number, 1 special char' | High | Boundary | Pass
TC_REG_005 | User Registration | Registration leaving mandatory fields blank | Registration page is open | 1. Navigate to Sign Up page 2. Leave all fields blank 3. Click 'Create Account' | All mandatory fields highlighted in red Error messages shown per field Form not submitted | Medium | Negative | Pass
📂 MODULE: User Login
TC_LOG_001 | User Login | Valid login with registered credentials | User account exists: john.doe@test.com / Test@1234 | 1. Navigate to Login page 2. Enter Email: john.doe@test.com 3. Enter Password: Test@1234 4. Click 'Login' | User logged in successfully Redirected to Home/Dashboard Username shown in header | Critical | Functional | Pass
TC_LOG_002 | User Login | Login with incorrect password | User account exists: john.doe@test.com | 1. Navigate to Login page 2. Enter Email: john.doe@test.com 3. Enter Password: WrongPass@1 4. Click 'Login' | Error: 'Invalid email or password. Please try again' Account not logged in | High | Negative | Pass
TC_LOG_003 | User Login | Account lockout after 5 failed login attempts | User account exists and is active | 1. Navigate to Login page 2. Enter correct email, wrong password 3. Repeat steps 5 times consecutively | After 5th attempt: 'Account temporarily locked for 30 minutes. Too many failed attempts' Lockout duration displayed | High | Security | Fail | Bug ID: BUG_003
TC_LOG_004 | User Login | Login with blank email and password | Login page is open | 1. Navigate to Login page 2. Leave Email and Password blank 3. Click 'Login' | Validation errors shown for both fields Form not submitted | Medium | Negative | Pass
TC_LOG_005 | User Login | Verify 'Remember Me' functionality | User account exists | 1. Navigate to Login page 2. Enter valid credentials 3. Check 'Remember Me' checkbox 4. Click Login 5. Close browser 6. Reopen browser and navigate to site | User remains logged in Session persisted across browser close | Medium | Functional | Pass
📂 MODULE: Product Search
TC_SRC_001 | Product Search | Search with valid product keyword | User is on homepage Products exist in catalogue | 1. Click on Search bar 2. Type 'Nike Running Shoes' 3. Press Enter or click Search icon | Search results page displayed Relevant products shown Product count displayed (e.g., '24 results') | Critical | Functional | Pass
TC_SRC_002 | Product Search | Search with non-existent product keyword | User is on homepage | 1. Click on Search bar 2. Type 'xyzproduct999' 3. Press Enter | Empty state shown: 'No products found for xyzproduct999' Suggestions or trending products shown | High | Negative | Pass
TC_SRC_003 | Product Search | Apply price range filter on search results | Search results page with products loaded | 1. Search for 'Shoes' 2. In filter panel, set Min Price: ₹500 3. Set Max Price: ₹2000 4. Click 'Apply Filters' | Only products between ₹500–₹2000 displayed Product count updates accordingly | High | Functional | Pass
TC_SRC_004 | Product Search | Sort search results by Price: Low to High | Search results page with products loaded | 1. Search for 'T-Shirts' 2. Click Sort dropdown 3. Select 'Price: Low to High' | Products re-sorted with lowest price first Sort order maintained on page navigation | Medium | Functional | Pass
📂 MODULE: Shopping Cart
TC_CRT_001 | Shopping Cart | Add single product to cart from product detail page | User is logged in Product page is open | 1. Navigate to product page (e.g., Blue Denim Jacket) 2. Select Size: M, Color: Blue 3. Ensure Quantity = 1 4. Click 'Add to Cart' | Product added to cart Cart icon count increases to 1 Success toast: 'Item added to your cart' Cart total updated | Critical | Functional | Pass
TC_CRT_002 | Shopping Cart | Update product quantity in cart | User is logged in Product exists in cart | 1. Navigate to Cart page 2. Find product row 3. Change quantity from 1 to 3 using + button 4. Observe cart total | Quantity updated to 3 Item subtotal = Price × 3 Cart total recalculated correctly | High | Functional | Pass
TC_CRT_003 | Shopping Cart | Remove product from cart | User is logged in At least 1 product in cart | 1. Navigate to Cart page 2. Click 'Remove' or trash icon on product 3. Confirm removal if prompted | Product removed from cart Cart total updated If last item removed: empty cart message shown | High | Functional | Pass
TC_CRT_004 | Shopping Cart | Apply valid coupon code in cart | User is logged in Cart has products Valid coupon SAVE20 (20% off) exists | 1. Navigate to Cart page 2. Scroll to Coupon section 3. Enter: SAVE20 4. Click 'Apply' | Coupon applied successfully Discount of 20% shown in order summary Success message: 'Coupon SAVE20 applied!' | High | Functional | Pass
TC_CRT_005 | Shopping Cart | Apply invalid/expired coupon code | User is logged in Cart has products | 1. Navigate to Cart page 2. Enter invalid code: EXPIRED50 3. Click 'Apply' | Error: 'Invalid or expired coupon code' No discount applied Total unchanged | Medium | Negative | Pass
📂 MODULE: Checkout Process
TC_CHK_001 | Checkout | Complete checkout with valid payment | User logged in Cart has 2 products Valid shipping address available | 1. Go to Cart → Click 'Proceed to Checkout' 2. Enter/Select delivery address 3. Choose shipping: Standard (Free) 4. Select Payment: Credit Card 5. Enter: 4111111111111111, CVV:123, Exp:12/27 6. Click 'Place Order' | Order placed successfully Order confirmation page shown with Order ID Confirmation email sent within 2 mins Inventory decremented | Critical | Functional | Pass
TC_CHK_002 | Checkout | Checkout without logging in (Guest checkout) | User is NOT logged in Cart has products | 1. Add product to cart as guest 2. Click 'Proceed to Checkout' 3. Enter email, shipping details 4. Complete payment | Guest checkout allowed Order placed with guest email Confirmation email sent | High | Functional | Pass
TC_CHK_003 | Checkout | Checkout with out-of-stock item in cart | Product in cart becomes out of stock before checkout | 1. Add product to cart 2. Product goes out of stock (admin action) 3. Proceed to checkout | Error shown: 'Some items in your cart are no longer available' Out-of-stock item highlighted Checkout blocked until resolved | High | Negative | Fail | Bug ID: BUG_008
📂 MODULE: Order Management
TC_ORD_001 | Order Management | View order history | User logged in At least 1 previous order exists | 1. Login to account 2. Go to Profile → My Orders 3. Observe order list | All past orders displayed with Order ID, Date, Status, Total Orders sorted by date (latest first) | High | Functional | Pass
TC_ORD_002 | Order Management | Cancel order in 'Processing' status | User logged in Order exists in 'Processing' status | 1. Go to My Orders 2. Select order in 'Processing' status 3. Click 'Cancel Order' 4. Select reason 5. Confirm | Order status changed to 'Cancelled' Refund initiated (if prepaid) Cancellation email sent | High | Functional | Pass
TC_ORD_003 | Order Management | Track order delivery status | User logged in Order exists in 'Shipped' status | 1. Go to My Orders 2. Select shipped order 3. Click 'Track Order' | Shipment tracking page opens Tracking ID and courier name shown Live tracking map/timeline visible | Medium | Functional | Pass

## 🐛 Bug Report
BUG REPORT — ShopEasy E-Commerce Website
Defect Log ¦ Manual Testing ¦ Sprint 1
Bug ID | Bug Title | Module | Severity | Priority | Status | Reported By | Steps to Reproduce | Expected Result | Actual Result | Assigned To | Date Reported | Date Resolved
BUG_001 | Login button unresponsive on Safari 17 | User Login | Minor | Low | Resolved | QA Engineer | 1. Open Safari 17 browser 2. Navigate to Login page 3. Enter valid credentials 4. Click 'Login' button | User should be logged in and redirected to dashboard | Login button does not respond on first click. Works on second click. Reproducible 100% on Safari 17 | Dev Team | 17-Feb-2026 | 19-Feb-2026
BUG_002 | Duplicate order placed on double-clicking 'Place Order' | Checkout | Critical | Critical | Open | QA Engineer | 1. Login and add product to cart 2. Go to checkout, fill all details 3. Double-click 'Place Order' button rapidly | Only 1 order should be placed. Button should be disabled after first click | 2 duplicate orders created with same products and payment charged twice | Backend Dev | 17-Feb-2026 | —
BUG_003 | Account not locked after 5 failed login attempts | User Login | High | High | Open | QA Engineer | 1. Navigate to Login page 2. Enter correct email, wrong password 5 times consecutively | Account should be locked for 30 minutes after 5 failed attempts with lockout message | No lockout occurs. User can attempt unlimited login tries. Security risk | Security Dev | 17-Feb-2026 | —
BUG_004 | Cart total not updating after removing coupon code | Shopping Cart | Medium | Medium | In Progress | QA Engineer | 1. Login and add products to cart 2. Apply coupon SAVE20 (discount applied) 3. Click 'Remove Coupon' | Cart total should revert to original price after coupon removal | Discount still shows even after removing coupon. Total not recalculated. Persists until page refresh | Frontend Dev | 17-Feb-2026 | —
BUG_005 | Product images not loading on Product Detail Page | Product Search | Major | High | Resolved | QA Engineer | 1. Search for 'Formal Shirts' 2. Click on any product 3. Observe product image gallery | Product images should load within 2 seconds. Image gallery should be functional | Broken image icons shown. Console error: 404 on image CDN path. Affects all products in 'Formal' category | DevOps / CDN | 17-Feb-2026 | 18-Feb-2026
BUG_006 | Wishlist count not updating in header after adding item | User Profile | Minor | Low | Resolved | QA Engineer | 1. Login to account 2. Navigate to any product 3. Click heart/wishlist icon | Wishlist count in header should increment immediately | Wishlist icon count does not update until page is manually refreshed | Frontend Dev | 17-Feb-2026 | 20-Feb-2026
BUG_007 | Order confirmation email contains wrong product image | Order Management | Medium | Medium | Open | QA Engineer | 1. Login and complete a purchase of 'Blue Denim Jacket' 2. Wait for confirmation email 3. Check product image in email | Email should display the correct image of 'Blue Denim Jacket' ordered | Email shows a different product image (Red T-Shirt). Wrong image URL mapped in email template | Backend Dev | 17-Feb-2026 | —
BUG_008 | Out-of-stock item allows checkout completion | Checkout | Critical | Critical | In Progress | QA Engineer | 1. Add product to cart 2. Admin marks product as out-of-stock 3. User proceeds to checkout 4. Completes payment | Checkout should be blocked with message: 'Item is no longer available' | Checkout proceeds successfully. Order placed for out-of-stock item. Stock shows negative value in DB | Backend Dev | 17-Feb-2026 | —
BUG_009 | Search bar accepts special characters causing 500 error | Product Search | High | High | Resolved | QA Engineer | 1. Go to homepage 2. In search bar, enter: <script>alert('XSS')</script> 3. Press Enter | Input should be sanitized. Safe error message shown. No script execution | Page returns HTTP 500 Internal Server Error. Potential XSS vulnerability identified | Security Dev | 17-Feb-2026 | 19-Feb-2026
BUG_010 | Price displayed in cart differs from product page price | Shopping Cart | Major | High | Open | QA Engineer | 1. Note product price on listing page: ₹1,299 2. Click product → Price on detail page: ₹1,299 3. Add to cart 4. View cart | Cart should show same price ₹1,299 as displayed on product pages | Cart shows ₹1,399 for same product. Price discrepancy of ₹100. Customer overcharged | Backend Dev | 17-Feb-2026 | —
BUG SUMMARY
Severity | Total | Open | Resolved | In Progress
Critical | 2 | 2 | 0 | 0
Major | 2 | 1 | 1 | 0
High | 3 | 2 | 1 | 0
Medium | 2 | 1 | 1 | 0
Minor | 1 | 0 | 1 | 0
TOTAL | 10 | 6 | 3 | 1

## 📊 RTM
REQUIREMENT TRACEABILITY MATRIX (RTM) — ShopEasy
Maps Business Requirements → Test Cases ¦ QA Portfolio
Req ID | Module | Requirement Description | Test Case ID(s) | TC Count | Executed | Passed | Failed
REQ_001 | User Registration | System shall allow users to register with email, name, and password | TC_REG_001, TC_REG_002, TC_REG_003, TC_REG_004, TC_REG_005 | 5 | 5 | 5 | 0
REQ_002 | User Registration | System shall validate email format and uniqueness during registration | TC_REG_002, TC_REG_003 | 2 | 2 | 2 | 0
REQ_003 | User Registration | Password must be minimum 8 characters with special char | TC_REG_004 | 1 | 1 | 1 | 0
REQ_004 | User Login | System shall authenticate user with email and password | TC_LOG_001, TC_LOG_002 | 2 | 2 | 2 | 0
REQ_005 | User Login | System shall lock account after 5 consecutive failed login attempts | TC_LOG_003 | 1 | 1 | 0 | 1
REQ_006 | User Login | System shall support 'Remember Me' session persistence | TC_LOG_005 | 1 | 1 | 1 | 0
REQ_007 | Product Search | System shall return relevant products based on keyword search | TC_SRC_001, TC_SRC_002 | 2 | 2 | 2 | 0
REQ_008 | Product Search | System shall allow users to filter products by price, category, brand | TC_SRC_003 | 1 | 1 | 1 | 0
REQ_009 | Product Search | System shall allow sorting of search results by price, rating | TC_SRC_004 | 1 | 1 | 1 | 0
REQ_010 | Shopping Cart | System shall allow adding products with size/color variants to cart | TC_CRT_001 | 1 | 1 | 1 | 0
REQ_011 | Shopping Cart | System shall allow updating quantity and removing items from cart | TC_CRT_002, TC_CRT_003 | 2 | 2 | 2 | 0
REQ_012 | Shopping Cart | System shall support coupon/promo code application | TC_CRT_004, TC_CRT_005 | 2 | 2 | 2 | 0
REQ_013 | Checkout | System shall support multiple payment methods for checkout | TC_CHK_001 | 1 | 1 | 1 | 0
REQ_014 | Checkout | System shall support guest checkout without account creation | TC_CHK_002 | 1 | 1 | 1 | 0
REQ_015 | Checkout | System shall prevent checkout for out-of-stock items | TC_CHK_003 | 1 | 1 | 0 | 1
REQ_016 | Order Management | System shall display order history with status and details | TC_ORD_001 | 1 | 1 | 1 | 0
REQ_017 | Order Management | System shall allow order cancellation for orders in 'Processing' state | TC_ORD_002 | 1 | 1 | 1 | 0
REQ_018 | Order Management | System shall provide real-time shipment tracking | TC_ORD_003 | 1 | 1 | 1 | 0
TOTAL / SUMMARY |  |  | 25 | 25 | 25 | 23 | 2
COVERAGE METRICS
Metric | Value
Total Requirements |  | 18
Total Test Cases Written |  | 25
Requirements Covered |  | 18 / 18 (100%)
Test Cases Executed |  | 25 / 25 (100%)
Pass Rate
Fail Rate
Blocked |  | 1 / 25 (3.70%)
Overall Coverage |  | 100% — All Requirements Traced

## 📈 Dashboard
QA TESTING DASHBOARD — ShopEasy E-Commerce
Sprint 1 Testing Summary ¦ Manual Testing Portfolio
TOTAL TEST CASES |  | ✅ PASSED |  | ❌ FAILED
25 |  | 23 |  | 2
Sprint 1 ¦ All Modules |  | 92% Pass Rate |  | 7.4% Fail Rate
🐛 TOTAL BUGS |  | 🔴 CRITICAL BUGS |  | 📋 REQUIREMENTS
10 |  | 2 |  | 18
All Severities |  | Immediate Fix Required |  | 100% Coverage
MODULE-WISE TESTING STATUS
Module | Total TCs | Passed | Failed | Pass % | Status
User Registration | 5 | 5 | 0 | 100.0% | ✅ Complete
User Login | 5 | 4 | 1 | 80.0% | ⚠️ Bug Open
Product Search | 4 | 4 | 0 | 100.0% | ✅ Complete
Shopping Cart | 5 | 5 | 0 | 100.0% | ✅ Complete
Checkout | 3 | 2 | 1 | 66.7% | ⚠️ Bug Open
Order Management | 3 | 3 | 0 | 100.0% | ✅ Complete
Admin Module | 2 | 2 | 0 | 100.0% | ✅ Complete
BUG STATUS BREAKDOWN
Severity | Total | Open | Resolved | In Progress | Remarks
🔴 Critical | 2 | 2 | 0 | 0 | Requires immediate fix
🟠 Major | 2 | 1 | 1 | 0 | 1 pending resolution
🟡 High | 3 | 2 | 1 | 0 | 2 open, monitoring
🔵 Medium | 2 | 1 | 0 | 1 | 1 in-progress
⚪ Minor | 1 | 0 | 1 | 0 | Resolved
TOTAL | 10 | 6 | 3 | 1 | 60% Open Rate